## Baoxiang Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 4 | 2 | 6(Decided the project topic) | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 6 | 4 | 2 | 2000-05-02 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 5，6 | 6
09/27 - 10/04 | 8 | 6 | 2 | 0 Learn unity. 1 Requirement analysis on meeting. 3. Implement Maps | 3 | 2 |  | 3 |  |  |  | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 0 Learn Unity. 2. Design Map 5 Communication | 3 |  | 3 |  |  | 2 |  | 2000-05-02 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 Learn Unity. 2. Design Maps. 3. Implement Maps 5 Communication | 2 |  | 2 | 2 |  | 2 |  | 0,2, 3,6 | 8

## Haotian Wu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 6 | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 10
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6
10/04-10/11 | 8 | 6 | 2 | 0 - Learn map design tool 2 - Design the maps 3 - Create the maps, add different objects(trees, houses and etc). Implement the movement of Tank. 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to camera movement 3 - Implement the camera set up (focus, auto zoom in/out) 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6

## Lei Yang
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 8 | 6 | 2 | 6(Decided the project topic) | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 6 | 2 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 6
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 0 - Learn unity development tool 2 - Design the tank shell 3 - implement fire function 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to shell explosion 3 - implement the shell explosion function 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6

## Qiwei Zheng
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 3 | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 | 1 | 0, 1, 3, 5 | 10
09/27 - 10/03 | 8 | 4 | 4 | 0- learned unity setup and model importing. learned pivotal tracker 1- More detail requirement design. 5 - basic tasks dispatching. | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0, 2, 5, 6 | 8
10/04-10/11 | 8 | 6 | 2 | 2- designing the maps and user interface 3 - create the maps and the add tank movement control 5 - merge changes | 0 | 0 | 3 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 3 - writing scripts for camera movement 5 - merge changes | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 0, 2, 3, 6

## Linlan Chen
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 4 | 2 |  | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0,1,5,6 | 6
09/18 - 09/22 | 6 | 4 | 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5,6 | 6
09/27 - 10/04 | 7 | 3 | 4 | 0 - Learn Unity set up and how to input projects and models. Follow the tutorials and play with the assets to get more familiar with Unity. Learn to use Pivotal Tracker and have a basic understanding of the process of project management. 1 - Detailed requirements analysis. 6- Some documentation. | 4 | 2 | 0 | 0 | 0 | 0 | 1 | 0,1,6 | 8
10/4-10/11 | 8 | 6 | 2 | 0 - Learn Unity development tools 2 - Do design based on user stories 5 - Communication 6 - Meeting Minutes | 3 | 0 | 2 | 0 | 0 | 2 | 1 | 0,3,5,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 3 - Implemented 2 map scenes 5 - Communication 6 - Meeting Minutes | 0 | 0 | 0 | 5 | 0 | 2 | 1 | 3,5,6

## Shuhan Liu
week # (from date - end date) | Total actual time of this week tasks (h) | Total Individual work time | Total meeting time | Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Estimated tasks for next week | Total estimated time
09/11 - 09/15 | 6 | 6 | 2 | 6(Decided the project topic) | [6 empty] | 6 | 0, 1, 2, 6 | 8
09/18 - 09/22 | 8 | 5 | 3 |  | 1 | 3 | 1 | 0 | 0 | 2 |  | 0, 1, 3, 5 | 6
09/27 - 10/04 | 8 | 4 | 4 | 0 - Learn unity set up, basic understanding of unity. Learn about pirvotal tracker as well. 1 - Confirm more details about each requirement. 5 - Basic task dispatching. | 4 | 2 | 0 | 0 | 0 | 2 |  | 0, 2, 5, 6
10/04-10/11 | 8 | 6 | 2 | 0 - Learn unity development tool 2 - Design the tank shell 3 - implement fire function 5 - Merge changes | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 3,6 | 8
10/11 - 10/17 | 8 | 6 | 2 | 0 - Learn knoledge that related to shell explosion 3 - implement the shell explosion function 5 - Merge changes | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 0, 2, 3, 6